## Web Film
T2207E4 - GROUP A - WEB FILM
# | Web Film | Start date | End date | Student | Status | Start Date | Member | Enrollment No.
| 1. DESIGN FIGMA | 2024-05-10 | 2024-05-12 |  | Work in progress | 13/05/2024 | Vu Xuan Du | Student1388712
| User Page | 2024-05-10 | 2024-05-11 | Nguyen Canh Hieu | Completed |  | Nguyen Manh Hieu
| Admin Page | 2024-05-11 | 2024-05-12 | Nguyen Canh Hieu | Work in progress | End Date | Nguyen Canh Hieu
[6 empty] | 20/07/2024 | Dong Van Thanh
| 2. DATABASE | 2024-05-13 | 2024-05-17 |  | Work in progress |  | Nguyen Khanh Duy
| Design DB | 2024-05-13 | 2024-05-15 | Nguyen Manh Hieu | Completed |  | Du + Hieu
| Add DB | 2024-05-15 | 2024-05-17 | Nguyen Canh Hieu | Work in progress
| Store Procedure | Cùng thời gian với module trong BE |  | Nguyen Canh Hieu | Work in progress
| 3. FE(DO IT ALWAYS IN MVC AND THE CORRESPONDING CONTROLLER) | 2024-05-10 | 2024-05-13 |  | Work in progress
| User Page | 2024-05-10 | 2024-05-11 | Vu Xuan Du | Completed
| Admin Page | 2024-05-11 | 2024-05-12 | Vu Xuan Du | Completed
| User Page - Fix | 2024-05-12 | 2024-05-13 | Vu Xuan Du | Work in progress
| Admin Page - Fix |  |  | Vu Xuan Du | Work in progress
| 4. Config Project | 2024-05-13 | 2024-05-15 | Vu Xuan Du | Work in progress
| 5. BE (HANDLING IN CONTROLLER) | 2024-05-15 | 2024-05-25 |  | Work in progress
Admin & User | Register | 2024-05-15 | 2024-05-16 | Nguyen Manh Hieu | Work in progress
| Login | 2024-05-16 | 2024-05-17 | Nguyen Manh Hieu | Work in progress
| Forgot Password | 2024-05-17 | 2024-05-19 | Nguyen Manh Hieu | Work in progress
| Reset Password | 2024-05-19 | 2024-05-20 | Nguyen Manh Hieu | Work in progress
| Login with Google | 2024-05-20 | 2024-05-22 | Nguyen Manh Hieu | Work in progress
| Notifications | 2024-05-22 | 2024-05-25 | Nguyen Manh Hieu | Work in progress
Admin | Category (of News) | 2024-05-15 | 2024-05-20 | Nguyen Khanh Duy | Work in progress
| News | 2024-05-20 | 2024-05-25 | Nguyen Khanh Duy | Work in progress
| Q&A | 2024-05-25 | 2024-06-01 | Nguyen Khanh Duy | Work in progress
| Actor | 2024-06-05 | 2024-06-15 | Nguyen Khanh Duy | Work in progress
| Writer | 2024-06-15 | 2024-06-25 | Nguyen Khanh Duy | Work in progress
| Director | 2024-05-15 | 2024-05-25 | Vu Xuan Du | Work in progress
| Genres | 2024-05-25 | 2024-06-01 | Vu Xuan Du | Work in progress
| Episodes | 2024-06-01 | 2024-06-05 | Vu Xuan Du | Work in progress
| Movies | 2024-06-05 | 2024-06-15 | Vu Xuan Du | Work in progress
| Buy Account | 2024-06-15 | 2024-06-25 | Vu Xuan Du | Work in progress
| Dashboard | 2024-06-25 | 2024-07-13 | Du + Hieu | Work in progress
User | Favourite | 2024-05-25 | 2024-06-01 | Nguyen Manh Hieu | Work in progress
| Rate | 2024-06-01 | 2024-06-05 | Nguyen Manh Hieu | Work in progress
| Review | 2024-06-05 | 2024-06-15 | Nguyen Manh Hieu | Work in progress
| Comment | 2024-06-15 | 2024-06-25 | Nguyen Manh Hieu | Work in progress
| Profile | 2024-05-15 | 2024-05-25 | Dong Van Thanh | Work in progress
| Search | 2024-05-25 | 2024-06-05 | Dong Van Thanh | Work in progress
| Follow Social Media | 2024-06-05 | 2024-06-15 | Dong Van Thanh | Work in progress
| All page of Footer | 2024-06-15 | 2024-07-13 | Dong Van Thanh | Work in progress
| 6. TEST | 2024-07-13 | 2024-07-16 |  | Work in progress
Admin & User | Register | 2024-07-13 | 2024-07-14 | Nguyen Khanh Duy | Work in progress
| Login |  |  | Nguyen Khanh Duy | Work in progress
| Login with Google |  |  | Nguyen Khanh Duy | Work in progress
| Forgot Password |  |  | Nguyen Khanh Duy | Work in progress
| Reset Password |  |  | Nguyen Khanh Duy | Work in progress
| Notifications |  |  | Nguyen Khanh Duy | Work in progress
Admin | Category (of News) | 2024-07-14 | 2024-07-15 | Dong Van Thanh | Work in progress
| News |  |  | Dong Van Thanh | Work in progress
| Q&A |  |  | Dong Van Thanh | Work in progress
| Actor |  |  | Dong Van Thanh | Work in progress
| Writer |  |  | Dong Van Thanh | Work in progress
| Director |  |  | Dong Van Thanh | Work in progress
| Genres |  |  | Dong Van Thanh | Work in progress
| Episodes |  |  | Dong Van Thanh | Work in progress
| Movies |  |  | Dong Van Thanh | Work in progress
| Dashboard |  |  | Dong Van Thanh | Work in progress
User | Profile | 2024-07-15 | 2024-07-16 | Nguyen Canh Hieu | Work in progress
| Search |  |  | Nguyen Canh Hieu | Work in progress
| Follow Social Media |  |  | Nguyen Canh Hieu | Work in progress
| Favourite |  |  | Nguyen Canh Hieu | Work in progress
| Rate |  |  | Nguyen Canh Hieu | Work in progress
| Review |  |  | Nguyen Canh Hieu | Work in progress
| Comment |  |  | Nguyen Canh Hieu | Work in progress
| All page of Footer |  |  | Nguyen Canh Hieu | Work in progress
| 7. MAKE REPORT | 2024-07-16 | 2024-07-19 | Dong Van Thanh | Work in progress
| 8. MAKE SLIDE | 2024-07-19 | 2024-07-20 | Dong Van Thanh | Work in progress
| 9. FIX ERRORS | 2024-07-20 | 2024-06-23 | Nguyen Manh Hieu | Work in progress
| 10. ENTIRE TEAM (1-2 days backup) | 2024-07-23 | 2024-07-25 | Vu Xuan Du | Work in progress